

|  |  |
| --- | --- |
| **ID** | 1 |
| **Name** | Stating the problem statement |
| **WBS #** | - |
| **Estimated duration** | 3 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 12/10/2018 |
| **End Date** | 15/10/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Clarifing the problem statement of the COMPANY MANAGEMENT SYSTEM and at the end to bring out a report about it |

|  |  |
| --- | --- |
| **ID** | 2 |
| **Name** | Prepation Of the Initial Plan |
| **WBS #** | - |
| **Estimated duration** | 3 day |
| **Predecessors** | 1,2 |
| **Successors** | - |
| **Start Date** | 24/10/2018 |
| **End Date** | 27/10/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Describing the overall picture of the COMPANY MANAGEMENT SYSTEM and at the end to bring out a report about it. |

|  |  |
| --- | --- |
| **ID** | 3 |
| **Name** | Update of the Initial Plan |
| **WBS #** | - |
| **Estimated duration** | 2 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 25/10/2018 |
| **End Date** | 27/10/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Revising the changes made to the Initial Plan of the COMPANY MANAGEMENT SYSTEM. |

|  |  |
| --- | --- |
| **ID** | 4 |
| **Name** | Prepation Of the SRS |
| **WBS #** | - |
| **Estimated duration** | 3 day |
| **Predecessors** | 3 |
| **Successors** | 6 |
| **Start Date** | 06/11/2018 |
| **End Date** | 09/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Presenting the detailed software requirements analysis for the  COMPANY MANAGEMENT SYSTEM and at the end to bring out a report about it. |

|  |  |
| --- | --- |
| **ID** | 5 |
| **Name** | Review meeting for the changes of software requirements  with the customer |
| **WBS #** | - |
| **Estimated duration** | 6 day |
| **Predecessors** | - |
| **Successors** | 8 |
| **Start Date** | 23/10/2018 |
| **End Date** | 29/10/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Reviewing the software requirements of the COMPANY MANAGEMENT SYSTEM to determine that if there is anything that the customer wants to add. |

|  |  |
| --- | --- |
| **ID** | 6 |
| **Name** | Preparation of managerial process plans |
| **WBS #** | - |
| **Estimated duration** | 5 day |
| **Predecessors** | 4,5 |
| **Successors** | 7,8 |
| **Start Date** | 01/11/2018 |
| **End Date** | 06/10/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing all of the managerial process plans that lies  below this work activity. |

|  |  |
| --- | --- |
| **ID** | 7 |
| **Name** | Work Plan |
| **WBS #** | - |
| **Estimated duration** | 5 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 05/11/2018 |
| **End Date** | 10/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Specifing the work activities, schedule, resources and budget  details for the COMPANY MANAGEMENT SYSTEM. |

|  |  |
| --- | --- |
| **ID** | 8 |
| **Name** | Control plans |
| **WBS #** | - |
| **Estimated duration** | 6 day |
| **Predecessors** | - |
| **Successors** | 11 |
| **Start Date** | 06/11/2018 |
| **End Date** | 12/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Specifing the reporting mechanisms and control procedures necessary to measure report and control the COMPANY MANAGEMENT SYSTEM. requirements, schedule, budget and recourses, the quality of work processes and work products. |

|  |  |
| --- | --- |
| **ID** | 9 |
| **Name** | Risk Management |
| **WBS #** | - |
| **Estimated duration** | 3 day |
| **Predecessors** | 7 |
| **Successors** | 12 |
| **Start Date** | 09/11/2018 |
| **End Date** | 12/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Specifing the risk management plan of COMPANY MANAGEMENT SYSTEM for identifying and analyzing risk factors. |

|  |  |
| --- | --- |
| **ID** | 10 |
| **Name** | Project Closeout Plan |
| **WBS #** | - |
| **Estimated duration** | 6 day |
| **Predecessors** | 8 |
| **Successors** | 13 |
| **Start Date** | 14/11/2018 |
| **End Date** | 20/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Containing the plans necessary to ensure orderly closeout of  the COMPANY MANAGEMENT SYSTEM. |

|  |  |
| --- | --- |
| **ID** | 11 |
| **Name** | Control of the project schedule |
| **WBS #** | - |
| **Estimated duration** | 1 day |
| **Predecessors** | 7,9 |
| **Successors** | 15,13 |
| **Start Date** | 12/11/2018 |
| **End Date** | 13/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Comparing actual progress to planned progress and to implement corrective action when actual progress does not  conform to planned progress. |

|  |  |
| --- | --- |
| **ID** | 12 |
| **Name** | Control of the budget requirements |
| **WBS #** | - |
| **Estimated duration** | 1 day |
| **Predecessors** | 9 |
| **Successors** | 14,18, |
| **Start Date** | 13/11/2018 |
| **End Date** | 14/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Comparing the planned cost to budgeted cost and implement corrective action when actual cost does not conform to  budgeted cost. |

|  |  |
| --- | --- |
| **ID** | 13 |
| **Name** | Review of the project risk factors |
| **WBS #** | - |
| **Estimated duration** | 1 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 15/11/2018 |
| **End Date** | 16/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Specifying ,analyzing and identifying the COMPANY MANAGEMENT SYSTEM risk factors |

|  |  |
| --- | --- |
| **ID** | 14 |
| **Name** | Review meeting for the content of the SPMP with the  Customer |
| **WBS #** | - |
| **Estimated duration** | 1 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 27/11/2018 |
| **End Date** | 28/10/2018 |
| **Personnel responsible** | Anıl Kuşçu,Gülfem Işık,Ebru Sarı |
| **Description** | Reviewing the SPMP’s content to determine that if there is  anything that the customer wants to add. |

|  |  |
| --- | --- |
| **ID** | 15 |
| **Name** | Preparation of technical process plans |
| **WBS #** | - |
| **Estimated duration** | 2 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 28/11/2018 |
| **End Date** | 30/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Gülfem Işık,Ebru Sarı |
| **Description** | Specifing the development process model, technical methods,  tools and techniques. |

|  |  |
| --- | --- |
| **ID** | 16 |
| **Name** | Preparation of supporting process plans |
| **WBS #** | - |
| **Estimated duration** | 1 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 29/11/2018 |
| **End Date** | 30/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Gülfem Işık,Ebru Sarı |
| **Description** | Containing plans for supporting processes that span the  duration of COMPANY MANAGEMENT SYSTEM. |

|  |  |
| --- | --- |
| **ID** | 17 |
| **Name** | Control of the quality of the SPMP |
| **WBS #** | - |
| **Estimated duration** | 1 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 29/11/2018 |
| **End Date** | 30/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Gülfem Işık,Ebru Sarı |
| **Description** | Comparing the actual quality level to the planned quality leveland implement corrective action when actual quality level does not conform to planned quality level. |

|  |  |
| --- | --- |
| **ID** | 18 |
| **Name** | Writing of the SPMP documentation |
| **WBS #** | - |
| **Estimated duration** | 5 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 02/12/2018 |
| **End Date** | 07/10/2018 |
| **Personnel responsible** | Anıl Kuşçu,Gülfem Işık,Ebru Sarı |
| **Description** | Documenting the activities that have been done for SPMP of  the COMPANY MANAGEMENT SYSTEM. |

|  |  |
| --- | --- |
| **ID** | 19 |
| **Name** | Review meeting for SPMP documentation |
| **WBS #** | - |
| **Estimated duration** | 3 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 05/12/2018 |
| **End Date** | 08/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Gülfem Işık,Ebru Sarı |
| **Description** | Reviewing the SPMP documentation. |

|  |  |
| --- | --- |
| **ID** | 20 |
| **Name** | Update of the SPMP documentation |
| **WBS #** | - |
| **Estimated duration** | 1 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 05/12/2018 |
| **End Date** | 06/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Gülfem Işık,Ebru Sarı |
| **Description** | Updating the SPMP documentation to do the necessary changes about the SPMP that is determined either at the Review meeting. |

|  |  |
| --- | --- |
| **ID** | 21 |
| **Name** | Review meeting for the changes of software requirements  with the customer |
| **WBS #** | - |
| **Estimated duration** | 1 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 07/12/2018 |
| **End Date** | 08/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Gülfem Işık,Ebru Sarı |
| **Description** | Reviewing the software requirements of the COMPANY MANAGEMENT SYSTEM to determine that if there is anything that the customer wants to add. |

|  |  |
| --- | --- |
| **ID** | 22 |
| **Name** | Preparation of the SDD |
| **WBS #** | - |
| **Estimated duration** | 3 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 07/12/2018 |
| **End Date** | 10/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Gülfem Işık,Ebru Sarı |
| **Description** | Symbolizing all of the SDD processes that lies below this  work activity. |

|  |  |
| --- | --- |
| **ID** | 23 |
| **Name** | Design of the COMPANY MANAGEMENT SYSTEM |
| **WBS #** | 1 |
| **Estimated duration** | 1 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 01/12/2018 |
| **End Date** | 02/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing all of the design processes that lies below this  work activity. |

|  |  |
| --- | --- |
| **ID** | 24 |
| **Name** | Design of the communication protocol between client &  server software |
| **WBS #** | 1 |
| **Estimated duration** | 2 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 01/12/2018 |
| **End Date** | 02/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Establishing a design for the communication protocol between the client software and server software to construct the communication protocol. |

|  |  |
| --- | --- |
| **ID** | 25 |
| **Name** | Design of the main interface |
| **WBS #** | 1.4 |
| **Estimated duration** | 2 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 02/12/2018 |
| **End Date** | 04/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Gülfem Işık,Ebru Sarı |
| **Description** | Designing html interface for main page |

|  |  |
| --- | --- |
| **ID** | 26 |
| **Name** | Design of the server software |
| **WBS #** | - |
| **Estimated duration** | 3 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 02/12/2018 |
| **End Date** | 05/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing all of the design processes for server software  that lies below this work activity. |

|  |  |
| --- | --- |
| **ID** | 27 |
| **Name** | Design of the manager page |
| **WBS #** | 1.1 |
| **Estimated duration** | 3 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 02/12/2018 |
| **End Date** | 05/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the design process for manager page |

|  |  |
| --- | --- |
| **ID** | 28 |
| **Name** | Design of the login page |
| **WBS #** | 1.1.2 |
| **Estimated duration** | 2 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 04/12/2018 |
| **End Date** | 06/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the design process for login page |

|  |  |
| --- | --- |
| **ID** | 29 |
| **Name** | Design of the add project |
| **WBS #** | 1.1.3 |
| **Estimated duration** | 1 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 02/12/2018 |
| **End Date** | 03/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the design process for add project |

|  |  |
| --- | --- |
| **ID** | 30 |
| **Name** | Design of the edit project |
| **WBS #** | 1.1.4 |
| **Estimated duration** | 1 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 06/12/2018 |
| **End Date** | 07/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the design process for edit project |

|  |  |
| --- | --- |
| **ID** | 31 |
| **Name** | Design of the delete user |
| **WBS #** | 1.1.5 |
| **Estimated duration** | 3 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 07/12/2018 |
| **End Date** | 10/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the design process for delete user |

|  |  |
| --- | --- |
| **ID** | 32 |
| **Name** | Design of the edit user |
| **WBS #** | 1.1.6 |
| **Estimated duration** | 3 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 07/12/2018 |
| **End Date** | 10/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the design process for edit user |

|  |  |
| --- | --- |
| **ID** | 33 |
| **Name** | Design of the delete comments |
| **WBS #** | 1.1.7 |
| **Estimated duration** | 1 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 10/12/2018 |
| **End Date** | 11/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the design process for delete comments |

|  |  |
| --- | --- |
| **ID** | 34 |
| **Name** | Design of the add comment |
| **WBS #** | 1.1.8/1.2.3/1.3.4 |
| **Estimated duration** | 1 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 09/12/2018 |
| **End Date** | 10/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the design process for add comment |

|  |  |
| --- | --- |
| **ID** | 35 |
| **Name** | Design of the customer page |
| **WBS #** | 1.2 |
| **Estimated duration** | 3 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 12/12/2018 |
| **End Date** | 15/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the design process for customer page |

|  |  |
| --- | --- |
| **ID** | 36 |
| **Name** | Design of the employee page |
| **WBS #** | 1.2.1 |
| **Estimated duration** | 3 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 17/12/2018 |
| **End Date** | 20/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the design process for employee page |

|  |  |
| --- | --- |
| **ID** | 37 |
| **Name** | Design of the employee information page |
| **WBS #** | 1.2.2/1.3.2 |
| **Estimated duration** | 2 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 18/12/2018 |
| **End Date** | 18/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the design process for employee information page |

|  |  |
| --- | --- |
| **ID** | 38 |
| **Name** | Control of the project schedule |
| **WBS #** | - |
| **Estimated duration** | 3 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 20/12/2018 |
| **End Date** | 23/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Comparing actual progress to planned progress and to implement corrective action when actual progress does not  conform to planned progress. |

|  |  |
| --- | --- |
| **ID** | 39 |
| **Name** | Control of the budget requirements |
| **WBS #** | - |
| **Estimated duration** | 1 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 20/12/2018 |
| **End Date** | 21/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Comparing the planned cost to budgeted cost and implement corrective action when actual cost does not conform to  budgeted cost. |

|  |  |
| --- | --- |
| **ID** | 40 |
| **Name** | Review of the project risk factors |
| **WBS #** | - |
| **Estimated duration** | 2 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 23/12/2018 |
| **End Date** | 25/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Specifying ,analyzing and identifying COMPANY MANAGEMENT SYSTEM risk factors |

|  |  |
| --- | --- |
| **ID** | 41 |
| **Name** | Review meeting for the content of the SDD with the customer |
| **WBS #** | - |
| **Estimated duration** | 3 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 22/12/2018 |
| **End Date** | 25/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Reviewing the SDD’s content to determine that if there is  anything that the customer wants to add. |

|  |  |
| --- | --- |
| **ID** | 42 |
| **Name** | Control of the quality of the SDD |
| **WBS #** | - |
| **Estimated duration** | 1 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 24/12/2018 |
| **End Date** | 25/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Comparing the actual quality level to the planned quality level and implement corrective action when actual quality level does not conform to planned quality level. |

|  |  |
| --- | --- |
| **ID** | 43 |
| **Name** | Writing of the SDD documentation |
| **WBS #** | - |
| **Estimated duration** | 1 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 24/12/2018 |
| **End Date** | 25/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Documenting the activities that have been done for SDD of  the COMPANY MANAGEMENT SYSTEM. |

|  |  |
| --- | --- |
| **ID** | 44 |
| **Name** | Review meeting for SDD documentation |
| **WBS #** | - |
| **Estimated duration** | 3 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 22/12/2018 |
| **End Date** | 25/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Reviewing the SDD documentation of the COMPANY MANAGEMENT SYSTEM |

|  |  |
| --- | --- |
| **ID** | 45 |
| **Name** | Update of the SDD documentation |
| **WBS #** | - |
| **Estimated duration** | 1 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 24/12/2018 |
| **End Date** | 25/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Updating the SDD documentation to do the necessary changes about the SDD. |

|  |  |
| --- | --- |
| **ID** | 46 |
| **Name** | Control of the quality of the SDD |
| **WBS #** | - |
| **Estimated duration** | 2 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 24/12/2018 |
| **End Date** | 26/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Controlling the updated SSD document of Company Management System |

|  |  |
| --- | --- |
| **ID** | 47 |
| **Name** | Writing of the SDD documentation |
| **WBS #** | - |
| **Estimated duration** | 2 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 24/12/2018 |
| **End Date** | 26/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Controlling the updated SSD document of Company Management System |

|  |  |
| --- | --- |
| **ID** | 48 |
| **Name** | Review meeting for SDD documentation |
| **WBS #** | - |
| **Estimated duration** | 1 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 24/12/2018 |
| **End Date** | 25/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Meeting for controlling SSD document of Company Management System |

|  |  |
| --- | --- |
| **ID** | 49 |
| **Name** | Update of the SDD documentation |
| **WBS #** | - |
| **Estimated duration** | 1 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 24/12/2018 |
| **End Date** | 25/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Update After meeting SSD document of Company Management System |

|  |  |
| --- | --- |
| **ID** | 50 |
| **Name** | Training for .net mvc language |
| **WBS #** | - |
| **Estimated duration** | 5 day |
| **Predecessors** | - |
| **Successors** | - |
| **Start Date** | 25/12/2018 |
| **End Date** | 30/12/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Training lecture for .net mvc framework |

|  |  |
| --- | --- |
| **ID** | 53 |
| **Name** | Coding of the COMPANY MANAGEMENT SYSTEM |
| **WBS #** | 1 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 24/10/2018 |
| **End Date** | 01/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing all of the coding process that lies below this  work activity. |

|  |  |
| --- | --- |
| **ID** | 54 |
| **Name** | Coding of the admin part |
| **WBS #** | 1.1 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık,Gülfem Işık,Ebru Sarı,Anıl Kuşçu |
| **Description** | Symbolizing all of the coding process that lies below this  work activity. |

|  |  |
| --- | --- |
| **ID** | 55 |
| **Name** | Coding of the login for admin |
| **WBS #** | 1.1.1 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 20/11/2018 |
| **End Date** | 27/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process for login admin |

|  |  |
| --- | --- |
| **ID** | 56 |
| **Name** | Coding of the add article |
| **WBS #** | 1.1.2 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process for add article |

|  |  |
| --- | --- |
| **ID** | 57 |
| **Name** | Coding of the delete article |
| **WBS #** | 1.1.3 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process for delete article |

|  |  |
| --- | --- |
| **ID** | 58 |
| **Name** | Approve Article |
| **WBS #** | 1.1.4 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process for approve article |

|  |  |
| --- | --- |
| **ID** | 59 |
| **Name** | Design of the delete user |
| **WBS #** | 1.1.5 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process for delete user |

|  |  |
| --- | --- |
| **ID** | 60 |
| **Name** | Coding of the approve comments |
| **WBS #** | 1.1.6 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process for approve comments |

|  |  |
| --- | --- |
| **ID** | 61 |
| **Name** | Design of the delete comments |
| **WBS #** | 1.1.7 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process for delete comments |

|  |  |
| --- | --- |
| **ID** | 62 |
| **Name** | Coding of the search article |
| **WBS #** | 1.1.8 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process for search article |

|  |  |
| --- | --- |
| **ID** | 63 |
| **Name** | Coding of the reader |
| **WBS #** | 1.2 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process for reader |

|  |  |
| --- | --- |
| **ID** | 64 |
| **Name** | Coding of the login reader |
| **WBS #** | 1.2.1 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process for login reader |

|  |  |
| --- | --- |
| **ID** | 65 |
| **Name** | Coding of the make comments |
| **WBS #** | 1.2.2 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process for make comments |

|  |  |
| --- | --- |
| **ID** | 66 |
| **Name** | Coding of the search for reader |
| **WBS #** | 1.2.3 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process search for reader |

|  |  |
| --- | --- |
| **ID** | 67 |
| **Name** | Coding of the writer |
| **WBS #** | 1.3 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process for writer |

|  |  |
| --- | --- |
| **ID** | 68 |
| **Name** | coding of the login for writer |
| **WBS #** | 1.3.1 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process for writer |

|  |  |
| --- | --- |
| **ID** | 69 |
| **Name** | Coding of the make comments |
| **WBS #** | 1.3.2 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process for make comments |

|  |  |
| --- | --- |
| **ID** | 70 |
| **Name** | coding of the article writer |
| **WBS #** | 1.3.3 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process for write article |

|  |  |
| --- | --- |
| **ID** | 71 |
| **Name** | Coding of the search for writer |
| **WBS #** | 1.3.4 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process search for writer |

|  |  |
| --- | --- |
| **ID** | 72 |
| **Name** | Coding of the user part |
| **WBS #** | 1.4 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process for user |

|  |  |
| --- | --- |
| **ID** | 73 |
| **Name** | Coding of the article readers for users |
| **WBS #** | 1.4.1 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the coding process for user article readers. |

|  |  |
| --- | --- |
| **ID** | 74 |
| **Name** | Control of the project schedule |
| **WBS #** | - |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Comparing actual progress to planned progress and to  implement corrective action when actual progress does not conform to planned progress. |

|  |  |
| --- | --- |
| **ID** | 75 |
| **Name** | Control of the budget requirement |
| **WBS #** | - |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Comparing the planned cost to budgeted cost and implement corrective action when actual cost does not conform to  budgeted cost. |

|  |  |
| --- | --- |
| **ID** | 76 |
| **Name** | Review of the project risk factors |
| **WBS #** | 1.0.0 |
| **Estimated duration** | 7 day |
| **Predecessors** | 4 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Specifying ,analyzing and identifying the COMPANY MANAGEMENT SYSTEM risk factors |

|  |  |
| --- | --- |
| **ID** | 77 |
| **Name** | Control of the quality of the code generated |
| **WBS #** | 1.0.1 |
| **Estimated duration** | 7 day |
| **Predecessors** | 5 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Comparing the actual quality level to the planned quality level and implement corrective action when actual quality level does not conform to planned quality level. |

|  |  |
| --- | --- |
| **ID** | 78 |
| **Name** | Training for testing processes |
| **WBS #** | 1.1.0 |
| **Estimated duration** | 7 day |
| **Predecessors** | 3 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Giving training Gülfem Işık,Ebru Sarı&Anıl Kuşçu by lectures and  discussions to make a background about testing techniques. |

|  |  |
| --- | --- |
| **ID** | 79 |
| **Name** | testing of the login for admin |
| **WBS #** | 1.1.1 |
| **Estimated duration** | 7 day |
| **Predecessors** | 2 |
| **Successors** | 6 |
| **Start Date** | 20/11/2018 |
| **End Date** | 27/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Gülfem Işık,Ebru Sarı |
| **Description** | Symbolizing the testing process for login admin |

|  |  |
| --- | --- |
| **ID** | 80 |
| **Name** | testing of the add article |
| **WBS #** | 1.1.2 |
| **Estimated duration** | 7 day |
| **Predecessors** | 4 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process for add article |

|  |  |
| --- | --- |
| **ID** | 81 |
| **Name** | testing of the delete article |
| **WBS #** | 1.1.3 |
| **Estimated duration** | 7 day |
| **Predecessors** | 3 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process for delete article |

|  |  |
| --- | --- |
| **ID** | 82 |
| **Name** | Approve Article |
| **WBS #** | 1.1.4 |
| **Estimated duration** | 7 day |
| **Predecessors** | 5 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process for approve article |

|  |  |
| --- | --- |
| **ID** | 83 |
| **Name** | Testing of the delete user |
| **WBS #** | 1.1.5 |
| **Estimated duration** | 7 day |
| **Predecessors** | 4 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process for delete user |

|  |  |
| --- | --- |
| **ID** | 84 |
| **Name** | testing of the approve comments |
| **WBS #** | 1.1.6 |
| **Estimated duration** | 7 day |
| **Predecessors** | 5 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process for approve comments |

|  |  |
| --- | --- |
| **ID** | 85 |
| **Name** | Design of the delete comments |
| **WBS #** | 1.1.7 |
| **Estimated duration** | 7 day |
| **Predecessors** | 3 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process for delete comments |

|  |  |
| --- | --- |
| **ID** | 86 |
| **Name** | testing of the search article |
| **WBS #** | 1.1.8 |
| **Estimated duration** | 7 day |
| **Predecessors** | 2 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process for search article |

|  |  |
| --- | --- |
| **ID** | 87 |
| **Name** | testing of the reader |
| **WBS #** | 1.2 |
| **Estimated duration** | 7 day |
| **Predecessors** | 4 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process for reader |

|  |  |
| --- | --- |
| **ID** | 88 |
| **Name** | testing of the login reader |
| **WBS #** | 1.2.1 |
| **Estimated duration** | 7 day |
| **Predecessors** | 5 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process for login reader |

|  |  |
| --- | --- |
| **ID** | 89 |
| **Name** | testing of the make comments |
| **WBS #** | 1.2.2 |
| **Estimated duration** | 7 day |
| **Predecessors** | 5 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process for make comments |

|  |  |
| --- | --- |
| **ID** | 90 |
| **Name** | testing of the search for reader |
| **WBS #** | 1.2.3 |
| **Estimated duration** | 7 day |
| **Predecessors** | 4 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process search for reader |

|  |  |
| --- | --- |
| **ID** | 91 |
| **Name** | testing of the writer |
| **WBS #** | 1.3 |
| **Estimated duration** | 7 day |
| **Predecessors** | 4 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process for writer |

|  |  |
| --- | --- |
| **ID** | 92 |
| **Name** | testing of the login for writer |
| **WBS #** | 1.3.1 |
| **Estimated duration** | 7 day |
| **Predecessors** | 2 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process for writer |

|  |  |
| --- | --- |
| **ID** | 93 |
| **Name** | testing of the make comments |
| **WBS #** | 1.3.2 |
| **Estimated duration** | 7 day |
| **Predecessors** | - |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process for make comments |

|  |  |
| --- | --- |
| **ID** | 94 |
| **Name** | testing of the article writer |
| **WBS #** | 1.3.3 |
| **Estimated duration** | 7 day |
| **Predecessors** | 4 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process for write article |

|  |  |
| --- | --- |
| **ID** | 95 |
| **Name** | testing of the search for writer |
| **WBS #** | 1.3.4 |
| **Estimated duration** | 7 day |
| **Predecessors** | 5 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process search for writer |

|  |  |
| --- | --- |
| **ID** | 96 |
| **Name** | testing of theuser part |
| **WBS #** | 1.4 |
| **Estimated duration** | 7 day |
| **Predecessors** | 2 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process for user |

|  |  |
| --- | --- |
| **ID** | 97 |
| **Name** | testing of the article readers for users |
| **WBS #** | 1.4.1 |
| **Estimated duration** | 7 day |
| **Predecessors** | 2 |
| **Successors** | 6 |
| **Start Date** | 02/11/2018 |
| **End Date** | 08/11/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Symbolizing the testing process for user article readers. |

|  |  |
| --- | --- |
| **ID** | 98 |
| **Name** | Delivery of initial product |
| **WBS #** | 1.4.2 |
| **Estimated duration** | 1 day |
| **Predecessors** | 5 |
| **Successors** | 6 |
| **Start Date** | 04/01/2018 |
| **End Date** | 04/01/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Determine the delivery of initial plan for COMPANY MANAGEMENT SYSTEM |

|  |  |
| --- | --- |
| **ID** | 99 |
| **Name** | Review meeting for the initial product with the customer |
| **WBS #** | 1.4.3 |
| **Estimated duration** | 1 day |
| **Predecessors** | 3 |
| **Successors** | 3 |
| **Start Date** | 04/01/2018 |
| **End Date** | 04/01/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Determining and controling initial product with the customer |

|  |  |
| --- | --- |
| **ID** | 100 |
| **Name** | Control of the project schedule |
| **WBS #** | 1.4.5 |
| **Estimated duration** | 1 day |
| **Predecessors** | 79 |
| **Successors** | 87 |
| **Start Date** | 04/01/2018 |
| **End Date** | 04/01/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Comparing actual progress to planned progress and to implement corrective action when actual progress does not conform to planned progress. |

|  |  |
| --- | --- |
| **ID** | 101 |
| **Name** | Control of the budget requirements |
| **WBS #** | 1.5.2 |
| **Estimated duration** | 1 day |
| **Predecessors** | 80 |
| **Successors** | 90 |
| **Start Date** | 04/01/2018 |
| **End Date** | 04/01/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Comparing the planned cost to budgeted cost and implement corrective action when actual cost does not conform to budgeted cost. |

|  |  |
| --- | --- |
| **ID** | 102 |
| **Name** | Review of the project risk factors |
| **WBS #** | 1.5.3 |
| **Estimated duration** | 1 day |
| **Predecessors** | 81 |
| **Successors** | 89 |
| **Start Date** | 04/01/2018 |
| **End Date** | 04/01/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Specifying ,analyzing and identifying the COMPANY MANAGEMENT SYSTEM risk factors |

|  |  |
| --- | --- |
| **ID** | 103 |
| **Name** | Control of the quality of the initial product |
| **WBS #** | 1.6 |
| **Estimated duration** | 1 day |
| **Predecessors** | 34 |
| **Successors** | 45 |
| **Start Date** | 04/01/2018 |
| **End Date** | 04/01/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Comparing the actual quality level to the planned quality level and implement corrective action when actual quality level does not conform to planned quality level. |

|  |  |
| --- | --- |
| **ID** | 104 |
| **Name** | Training for IEEE Std. 1063-1987 |
| **WBS #** | 1.6.1 |
| **Estimated duration** | 1 day |
| **Predecessors** | 23 |
| **Successors** | 25 |
| **Start Date** | 05/01/2018 |
| **End Date** | 05/01/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Giving training to Anıl Kuşçu & Gülfem Işık,Ebru Sarı by lectures and discussions to make a background about IEEE Std. 1063- 1987 |

|  |  |
| --- | --- |
| **ID** | 105 |
| **Name** | Preparation of the User Manual |
| **WBS #** | 1.6.2 |
| **Estimated duration** | 1 day |
| **Predecessors** | 13 |
| **Successors** | 17 |
| **Start Date** | 04/01/2018 |
| **End Date** | 04/01/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Describing how the COMPANY MANAGEMENT SYSTEM is working and at the end to bring out a report about it. |

|  |  |
| --- | --- |
| **ID** | 106 |
| **Name** | Product Demonstration |
| **WBS #** | 1.6.3 |
| **Estimated duration** | 1 day |
| **Predecessors** | 8 |
| **Successors** | 9 |
| **Start Date** | 04/01/2018 |
| **End Date** | 04/01/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Showing the final product to the customer. |

|  |  |
| --- | --- |
| **ID** | 107 |
| **Name** | Delivery of the final product |
| **WBS #** | 1.6.4 |
| **Estimated duration** | 1 day |
| **Predecessors** | 3 |
| **Successors** | 4 |
| **Start Date** | 04/01/2018 |
| **End Date** | 04/01/2018 |
| **Personnel responsible** | Anıl Kuşçu,Ebru Sarı,Gülfem Işık |
| **Description** | Submitting the final product to the customer |

|  |  |
| --- | --- |
|  | **Work Activity** |
|  | Stating the problem statement |
|  | Preparation of the Initial Plan |
|  | Preparation of the SRS |
|  | Review meeting for the changes of software requirements with the customer |
|  | Preparation of the SPMP |
|  | Update of the Initial Plan |
|  | Preparation of managerial process plans |
|  | Work plan |
|  | Control Plan |
|  | Risk management plan |
|  | Project closeout plan |
|  | Control of the project schedule |
|  | Control of the budget requirements |
|  | Review of the project risk factors |
|  | Review meeting for the content of the SPMP with the customer |
|  | Preparation of technical process plans |
|  | Preparation of supporting process plans |
|  | Control of the quality of the SPMP |
|  | Writing of the SPMP documentation |
|  | Review meeting for SPMP documentation |
|  | Update of the SPMP documentation |
|  | Training for IEEE Std. 1016-1998 |
|  | Review meeting for the changes of software requirements with the customer |
|  | Preparation of the SDD |
|  | Design of the Company Management System |
|  | Design of the communication protocol between client & server softwares |
|  | Design of the main interface |
|  | Design of the server software |
|  | Design of the manager page |
|  | Design of the login page |
|  | Design of the add project |
|  | Design of the edit project |
|  | Design of the delete project |
|  | Design of the add user |
|  | Design of the delete user |
|  | Design of the edit user |
|  | Design of the delete comments |
|  | Design of the add comments |
|  | Design of the customer page |
|  | Design of the employee page |
|  | Design of the employee information page |
|  | Design of the customer information page |
|  | Control of the project schedule |
|  | Control of the budget requirements |
|  | Review of the project risk factors |
|  | Review meeting for the content of the SDD with the customer |
|  | Control of the quality of the SDD |
|  | Writing of the SDD documentation |
|  | Review meeting for SDD documentation |
|  | Update of the SDD documentation |
|  | Training for .net mvc language |
|  | Coding of the main interface |
|  | Coding of the server software |
|  | Coding of the manager page |
|  | Coding of the login page |
|  | Coding of the add project |
|  | Coding of the edit project |
|  | Coding of the delete project |
|  | Coding of the add user |
|  | Coding of the delete user |
|  | Coding of the edit user |
|  | Coding of the delete comments |
|  | Coding of the add comments |
|  | Coding of the customer page |
|  | Coding of the employee page |
|  | Coding of the employee information page |
|  | Coding of the customer information page |
|  | Coding of the main interface |
|  | Coding of the server software |
|  | Coding of the manager page |
|  | Coding of the login page |
|  | Coding of the add project |
|  | Coding of the edit project |
|  | Coding of the delete project |
|  | Control of the project schedule |
|  | Control of the budget requirements |
|  | Review of the project risk factors |
|  | Control of the quality of the code generated |
|  | Training for testing processes |
|  | Testing of the main interface |
|  | Testing of the server software |
|  | Testing of the manager page |
|  | Testing of the login page |
|  | Testing of the add project |
|  | Testing of the edit project |
|  | Testing of the delete project |
|  | Testing of the add user |
|  | Testing of the delete user |
|  | Testing of the edit user |
|  | Testing of the delete comments |
|  | Testing of the add comments |
|  | Testing of the customer page |
|  | Testing of the employee page |
|  | Testing of the employee information page |
|  | Testing of the customer information page |
|  | Testing of the main interface |
|  | Testing of the server software |
|  | Delivery of initial product |
|  | Review meeting for the initial product with the customer |
|  | Control of the project schedule |
|  | Control of the budget requirements |
|  | Review of the project risk factors |
|  | Control of the quality of the initial product |
|  | Training for IEEE Std. 1063-1987 |
|  | Preparation of the User Manual |
|  | Product Demonstration |
|  | Delivery of the final product |

**Resource Allocation**

|  |  |
| --- | --- |
| Name | Stating the problem statement |
| WBS# | 1 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Preparation of the Initial Plan |
| WBS# | 2 |
| Personnel responsible | Anıl KUŞÇU, Ebru SARI |

|  |  |
| --- | --- |
| Name | Preparation of the SRS |
| WBS# | 3 |
| Personnel responsible | Ebru SARI, Gülfem IŞIK |

|  |  |
| --- | --- |
| Name | Review meeting for the changes of software requirements with the customer |
| WBS# | 4 |
| Personnel responsible | Gulfem IŞIK, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Preparation of the SPMP |
| WBS# | 5 |
| Personnel responsible | All of the member |

|  |  |
| --- | --- |
| Name | Update of the Initial Plan |
| WBS# | 6 |
| Personnel responsible | Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Preparation of managerial process plans |
| WBS# | 7 |
| Personnel responsible | Ebru SARI |

|  |  |
| --- | --- |
| Name | Work plan |
| WBS# | 8 |
| Personnel responsible | Gülfem IŞIK |

|  |  |
| --- | --- |
| Name | Control Plan |
| WBS# | 9 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Risk management plan |
| WBS# | 10 |
| Personnel responsible | Anıl KUŞÇU, Gülfem IŞIK |

|  |  |
| --- | --- |
| Name | Project closeout plan |
| WBS# | 11 |
| Personnel responsible | Ebru SARI, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Control of the project schedule |
| WBS# | 12 |
| Personnel responsible | Gülfem IŞIK, Ebru SARI |

|  |  |
| --- | --- |
| Name | Control of the budget requirements |
| WBS# | 13 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Review of the project risk factors |
| WBS# | 14 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Review meeting for the content of the SPMP with the customer |
| WBS# | 15 |
| Personnel responsible | Gülfem IŞIK |

|  |  |
| --- | --- |
| Name | Preparation of technical process plans |
| WBS# | 16 |
| Personnel responsible | Ebru SARI |

|  |  |
| --- | --- |
| Name | Preparation of supporting process plans |
| WBS# | 17 |
| Personnel responsible | Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Control of the quality of the SPMP |
| WBS# | 18 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Writing of the SPMP documentation |
| WBS# | 19 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Review meeting for SPMP documentation |
| WBS# | 20 |
| Personnel responsible | Gülfem IŞIK, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Training for IEEE Std. 1016-1998 |
| WBS# | 21 |
| Personnel responsible | Ebru Sarı, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Training for IEEE Std. 1016-1998 |
| WBS# | 22 |
| Personnel responsible | Gülfem IŞIK, Ebru SARI |

|  |  |
| --- | --- |
| Name | Review meeting for the changes of software requirements with the customer |
| WBS# | 23 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Preparation of the SDD |
| WBS# | 24 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Design of the Company Management System |
| WBS# | 25 |
| Personnel responsible | Ebru SARI |

|  |  |
| --- | --- |
| Name | Update of the Initial Plan |
| WBS# | 26 |
| Personnel responsible | Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Design of the main interface |
| WBS# | 27 |
| Personnel responsible | Gülfem IŞIK |

|  |  |
| --- | --- |
| Name | Design of the server software |
| WBS# | 28 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Design of the manager page |
| WBS# | 29 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Design of the login page |
| WBS# | 30 |
| Personnel responsible | Gülfem IŞIK, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Design of the add project |
| WBS# | 31 |
| Personnel responsible | Ebru SARI, Gülfem IŞIK |

|  |  |
| --- | --- |
| Name | Design of the edit project |
| WBS# | 32 |
| Personnel responsible | Anıl KUŞÇU, Ebru SARI |

|  |  |
| --- | --- |
| Name | Design of the delete project |
| WBS# | 33 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Design of the add user |
| WBS# | 34 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Design of the delete user |
| WBS# | 35 |
| Personnel responsible | Gülfem IŞIK |

|  |  |
| --- | --- |
| Name | Design of the edit user |
| WBS# | 36 |
| Personnel responsible | Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Design of the delete comments |
| WBS# | 37 |
| Personnel responsible | Ebru SARI |

|  |  |
| --- | --- |
| Name | Design of the add comments |
| WBS# | 38 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Design of the customer page |
| WBS# | 39 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Design of the employee page |
| WBS# | 40 |
| Personnel responsible | Gülfem IŞIK, Ebru SARI |

|  |  |
| --- | --- |
| Name | Design of the employee page |
| WBS# | 41 |
| Personnel responsible | Gülfem IŞIK, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Design of the customer information page |
| WBS# | 42 |
| Personnel responsible | Anıl KUŞÇU, Ebru SARI |

|  |  |
| --- | --- |
| Name | Control of the project schedule |
| WBS# | 43 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Control of the budget requirements |
| WBS# | 44 |
| Personnel responsible | Gülfem IŞIK |

|  |  |
| --- | --- |
| Name | Review of the project risk factors |
| WBS# | 45 |
| Personnel responsible | Ebru SARI |

|  |  |
| --- | --- |
| Name | Review meeting for the content of the SDD with the customer |
| WBS# | 46 |
| Personnel responsible | Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Control of the quality of the SDD |
| WBS# | 47 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Writing of the SDD documentation |
| WBS# | 48 |
| Personnel responsible | Ebru SARI, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Review meeting for SDD documentation |
| WBS# | 49 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Update of the SDD documentation |
| WBS# | 50 |
| Personnel responsible | Gülfem IŞIK |

|  |  |
| --- | --- |
| Name | Training for .net mvc language |
| WBS# | 51 |
| Personnel responsible | Ebru SARI |

|  |  |
| --- | --- |
| Name | Coding of the main interface |
| WBS# | 52 |
| Personnel responsible | Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Coding of the server software |
| WBS# | 53 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Coding of the manager page |
| WBS# | 54 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Coding of the login page |
| WBS# | 55 |
| Personnel responsible | Gülfem IŞIK, Ebru SARI |

|  |  |
| --- | --- |
| Name | Coding of the add project |
| WBS# | 56 |
| Personnel responsible | Anıl KUŞÇU, Ebru SARI |

|  |  |
| --- | --- |
| Name | Coding of the edit project |
| WBS# | 57 |
| Personnel responsible | Gülfem IŞIK, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Coding of the delete project |
| WBS# | 58 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Coding of the add user |
| WBS# | 59 |
| Personnel responsible | Gülfem IŞIK |

|  |  |
| --- | --- |
| Name | Coding of the delete user |
| WBS# | 60 |
| Personnel responsible | Ebru SARI |

|  |  |
| --- | --- |
| Name | Coding of the edit user |
| WBS# | 61 |
| Personnel responsible | Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Coding of the delete comments |
| WBS# | 62 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Coding of the add comments |
| WBS# | 63 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Coding of the customer page |
| WBS# | 64 |
| Personnel responsible | Gülfem IŞIK, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Coding of the employee page |
| WBS# | 65 |
| Personnel responsible | Gülfem IŞIK, Ebru SARI |

|  |  |
| --- | --- |
| Name | Coding of the employee information page |
| WBS# | 66 |
| Personnel responsible | Ebru SARI, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Coding of the customer information page |
| WBS# | 67 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Coding of the main interface |
| WBS# | 68 |
| Personnel responsible | Gülfem IŞIK |

|  |  |
| --- | --- |
| Name | Coding of the server software |
| WBS# | 69 |
| Personnel responsible | Ebru SARI |

|  |  |
| --- | --- |
| Name | Coding of the manager page |
| WBS# | 70 |
| Personnel responsible | Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Coding of the login page |
| WBS# | 71 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Coding of the add project |
| WBS# | 72 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Coding of the edit project |
| WBS# | 73 |
| Personnel responsible | Ebru SARI, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Coding of the delete project |
| WBS# | 74 |
| Personnel responsible | Gülfem IŞIK, Ebru SARI |

|  |  |
| --- | --- |
| Name | Control of the project schedule |
| WBS# | 75 |
| Personnel responsible | Gülfem IŞIK, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Control of the budget requirements |
| WBS# | 76 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Review of the project risk factors |
| WBS# | 77 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Control of the quality of the code generated |
| WBS# | 78 |
| Personnel responsible | Gülfem IŞIK |

|  |  |
| --- | --- |
| Name | Training for testing processes |
| WBS# | 79 |
| Personnel responsible | Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Testing of the main interface |
| WBS# | 80 |
| Personnel responsible | Ebru SARI |

|  |  |
| --- | --- |
| Name | Testing of the server software |
| WBS# | 81 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Testing of the manager page |
| WBS# | 82 |
| Personnel responsible | Gülfem IŞIK, Ebru SARI |

|  |  |
| --- | --- |
| Name | Testing of the manager page |
| WBS# | 83 |
| Personnel responsible | Ebru SARI, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Testing of the add project |
| WBS# | 84 |
| Personnel responsible | Gülfem IŞIK, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Testing of the edit project |
| WBS# | 85 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Testing of the delete project |
| WBS# | 86 |
| Personnel responsible | Gülfem IŞIK |

|  |  |
| --- | --- |
| Name | Testing of the add user |
| WBS# | 87 |
| Personnel responsible | Ebru SARI |

|  |  |
| --- | --- |
| Name | Testing of the delete user |
| WBS# | 88 |
| Personnel responsible | Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Testing of the edit user |
| WBS# | 89 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Testing of the delete comments |
| WBS# | 90 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Testing of the add comments |
| WBS# | 91 |
| Personnel responsible | Gülfem IŞIK, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Testing of the customer page |
| WBS# | 92 |
| Personnel responsible | Gülfem IŞIK, Ebru SARI |

|  |  |
| --- | --- |
| Name | Testing of the employee page |
| WBS# | 93 |
| Personnel responsible | Ebru SARI, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Testing of the employee information page |
| WBS# | 94 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Testing of the customer information page |
| WBS# | 95 |
| Personnel responsible | Gülfem IŞIK |

|  |  |
| --- | --- |
| Name | Testing of the main interface |
| WBS# | 96 |
| Personnel responsible | Ebru SARI |

|  |  |
| --- | --- |
| Name | Testing of the server software |
| WBS# | 97 |
| Personnel responsible | Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Delivery of initial product |
| WBS# | 98 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Review meeting for the initial product with the customer |
| WBS# | 99 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Control of the project schedule |
| WBS# | 100 |
| Personnel responsible | Gülfem IŞIK, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Control of the budget requirements |
| WBS# | 101 |
| Personnel responsible | Ebru SARI, Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Review of the project risk factors |
| WBS# | 102 |
| Personnel responsible | Gülfem IŞIK, Ebru SARI |

|  |  |
| --- | --- |
| Name | Control of the quality of the initial product |
| WBS# | 103 |
| Personnel responsible | All of the members |

|  |  |
| --- | --- |
| Name | Training for IEEE Std. 1063-1987 |
| WBS# | 104 |
| Personnel responsible | Gülfem IŞIK |

|  |  |
| --- | --- |
| Name | Preparation of the User Manual |
| WBS# | 105 |
| Personnel responsible | Ebru SARI |

|  |  |
| --- | --- |
| Name | Product Demonstration |
| WBS# | 106 |
| Personnel responsible | Anıl KUŞÇU |

|  |  |
| --- | --- |
| Name | Delivery of the final product |
| WBS# | 107 |
| Personnel responsible | All of the members |